## Tabelle1
Module | Scope | Phase | Task | Description | Comment | Effort | Costs | Base | Base Descriptor | Multiplier1 | Multiplier1 Descriptor | Multiplier2 | Multiplier2 Descriptor | 1d Trips | 2d Trips | 3d Trips | 4d Trips | 5d Trips
MIC CCS | Basic Setup | Design | 2 Workshops à 2 days |  | 2 days preparation and wrap up | 6 | 9120 | 2 | workshops | 2 | days | 1 | MIC expert(s) |  | 2
MIC CCS | Basic Setup | Design | Process Description |  |  | 4 | 6080
MIC CCS | Basic Setup | Design | Functional Specification |  |  | 3 | 4560
MIC CCS | Basic Setup | Installation & configuration on test & production environment | Setup of MIC CCS on test environment |  |  | 1 | 1360
MIC CCS | Basic Setup | Installation & configuration on test & production environment | Setup of MIC CCS on production environment |  |  | 0.5 | 680
MIC CCS | Basic Setup | Installation & configuration on test & production environment | Configuration of master data on test environment |  | Assumption 1 company/plant combination | 1 | 1360
MIC CCS | Basic Setup | Installation & configuration on test & production environment | Configuration of master data on production environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC CCS | Basic Setup | Installation & configuration on test & production environment | Setup of user and security settings on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC CCS | Basic Setup | Installation & configuration on test & production environment | Setup of user and security settings on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC CCS | Basic Setup | Installation & configuration on test & production environment | Configuration of MIC-GTCS for global trade content services Tariff master |  |  | 1 | 1360
MIC CCS | Basic Setup | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC CCS | Basic Setup | Integration tests | Support during integration tests |  |  | 1 | 1360
MIC CCS | Basic Setup | Overall business process test on test & production environment | Definition of test cases |  |  | 1 | 1360
MIC CCS | Basic Setup | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 2 | 2720
MIC CCS | Basic Setup | Data Migration | Migration of Part Master Data |  | Assumption: Master Data will be provided in MIC specified CSV/XLS format | 1.5 | 2040
MIC CCS | Basic Setup | Training and Go-Live Support | CWT (Client Walk Through) - MIC CCS - Key User |  | Assumption: not needed; covered with user training | 0 | 0
MIC CCS | Basic Setup | Training and Go-Live Support | Key User Training - MIC-CCS |  | Assumption: on-site (0,5 out of 1,5 days are for preparation and wrap-up activities), 1 trip estimated | 1.5 | 1920 |  |  | 1.5 | days |  |  | 1
MIC CCS | Basic Setup | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC CCS Key User |  | Assumption: 2 weeks 1 day per week | 2 | 2560 |  |  | 2 | weeks | 1 | day per week
MIC CCS | Basic Setup | Training and Go-Live Support | Go-Live Support - MIC CCS |  | Assumption: done remote; Remaining efforts are covered by country rollout which is done for min. 1 country in parallel | 1 | 1280
MIC CCS | Basic Setup | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC CCS | Basic Setup Part Master | Design | Requirements Definition |  | Assumption: no workshop needed | 0 | 0
MIC CCS | Basic Setup Part Master | Design | Process Design & Description |  |  | 2 | 3040
MIC CCS | Basic Setup Part Master | Installation & configuration on test & production environment | Setup of MIC CCS on test & production environment |  |  | 1 | 1360
MIC CCS | Basic Setup Part Master | Installation & configuration on test & production environment | Configuration of master data on test & production environment |  | Assumption 1 company/plant combination | 1 | 1360
MIC CCS | Basic Setup Part Master | Installation & configuration on test & production environment | Setup of user and security settings on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC CCS | Basic Setup Part Master | Installation & configuration on test & production environment | Configuration of MIC-GTCS for global trade content services Tariff master |  |  | 1 | 1360
MIC CCS | Basic Setup Part Master | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional cost | 0 | 0
MIC CCS | Basic Setup Part Master | Integration tests | Support during integration tests |  | Assumption: covered with interfaces | 0 | 0
MIC CCS | Basic Setup Part Master | Overall business process test on test & production environment | Definition of test cases |  |  | 0.5 | 680
MIC CCS | Basic Setup Part Master | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 1 | 1360
MIC CCS | Basic Setup Part Master | Data Migration | Migration of Part Master Data |  | Assumption: Master Data will be provided in MIC specified CSV/XLS format | 1.5 | 2040
MIC CCS | Basic Setup Part Master | Training and Go-Live Support | CWT (Client Walk Through) - MIC CCS - Key User |  | Assumption: not needed; covered with user training | 0 | 0
MIC CCS | Basic Setup Part Master | Training and Go-Live Support | Key User Training - MIC-CCS |  | Assumption: 1,0 out of 1,5 days are for preparation and wrap-up activities, Training on-site (combined with other trainings) or remote | 1.5 | 1920 |  |  | 1.5 | days
MIC CCS | Basic Setup Part Master | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC CCS Key User |  | Assumption: 2 weeks 1 day per week | 2 | 2560 |  |  | 2 | weeks | 1 | day per week
MIC CCS | Basic Setup Part Master | Training and Go-Live Support | Go-Live Support - MIC CCS |  | Assumption: done remote; Remaining efforts are covered by country rollout which is done for min. 1 country in parallel | 1 | 1280
MIC CCS | Basic Setup Part Master | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC CCS CTC | Per Country | Installation & configuration on test & production environment | Configuration of master data MIC CCS CTC for country on test environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC CCS CTC | Per Country | Installation & configuration on test & production environment | Setup of user and security settings for country on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC CCS CTC | Per Country | Installation & configuration on test & production environment | Configuration of master data MIC CCS CTC for country on production environment |  |  | 0.5 | 680
MIC CCS CTC | Per Country | Installation & configuration of interfaces on test- and production environment | Configuration of existing interface to upload data for country |  |  | 0.5 | 680
MIC CCS CTC | Per Country | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC CCS CTC | Per Country | Data migration |  |  | Assumption: data will be uploaded via interfaces (no manual migration required) | 0 | 0
MIC CCS CTC | Per Country | Overall business process test on test & production environment | Definition of test cases |  |  | 0.5 | 680
MIC CCS CTC | Per Country | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 2 | 2720
MIC CCS CTC | Per Country | Training and Go-Live Support | CWT (Client Walk Through) - MIC CCS - Key User |  | Assumption: not needed; covered with user training | 0 | 0
MIC CCS CTC | Per Country | Training and Go-Live Support | Key User Training - MIC CCS |  | Assumption: already inlcuded in basic setup efforts | 0 | 0
MIC CCS CTC | Per Country | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC CCS Key User |  | Assumption: already inlcuded in basic setup efforts | 0 | 0
MIC CCS CTC | Per Country | Training and Go-Live Support | Go-Live Support - MIC CCS CTC - Key User |  | Assumption: done remotely | 0.5 | 640
MIC CCS CTC | Per Country | Training and Go-Live Support | Service Transition |  |  |  | 0
MIC DPS | Denied Party Screening | Design | Workshop |  | 1 workshop à 1 day; 0,5 days preparation and wrap up, 1 trip estimated | 1.5 | 2280 | 1 | workshop | 1 | day |  |  | 1
MIC DPS | Denied Party Screening | Design | Process Description |  |  | 1 | 1520
MIC DPS | Denied Party Screening | Design | Functional Specification |  |  | 0.5 | 760
MIC DPS | Denied Party Screening | Installation & configuration on test & production environment | Setup of MIC DPS on test environment |  |  | 1 | 1360
MIC DPS | Denied Party Screening | Installation & configuration on test & production environment | Setup of MIC DPS on production environment |  |  | 0.5 | 680
MIC DPS | Denied Party Screening | Installation & configuration on test & production environment | Configuration of master data on test environment |  | Assumption 1 company/plant combination | 1 | 1360
MIC DPS | Denied Party Screening | Installation & configuration on test & production environment | Configuration of master data on production environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC DPS | Denied Party Screening | Installation & configuration on test & production environment | Setup of user and security settings on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC DPS | Denied Party Screening | Installation & configuration on test & production environment | Setup of user and security settings on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC DPS | Denied Party Screening | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC DPS | Denied Party Screening | Integration tests | Support during integration tests |  |  | 2 | 2720
MIC DPS | Denied Party Screening | Overall business process test on test & production environment | Definition of test cases |  |  | 0.5 | 680
MIC DPS | Denied Party Screening | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 1 | 1360
MIC DPS | Denied Party Screening | Training and Go-Live Support | CWT (Client Walk Through) - MIC DPS - Key User |  | Assumption: not needed; covered with user training | 0 | 0
MIC DPS | Denied Party Screening | Training and Go-Live Support | Key User Training - MIC DPS incl. electronic documentation |  | 0,5 out of 1 days are for preparation and wrap-up activities | 1 | 1280 |  |  | 1 | day
MIC DPS | Denied Party Screening | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC DPS - Key User |  | Assumption: 1 week 0,5 days per week | 0.5 | 640 |  |  | 1 | week | 0.5 | days per week
MIC DPS | Denied Party Screening | Training and Go-Live Support | Go-Live Support - MIC DPS |  | Assumption: done remotely | 0.5 | 640
MIC DPS | Denied Party Screening | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC ECM | Basic Setup | Design | 2 workshops à 2 days |  | 2 days preparation and wrap up, 2 trips estimated | 6 | 9120 | 2 | workshops | 2 | days |  |  |  | 2
MIC ECM | Basic Setup | Design | Process Description |  |  | 4 | 6080
MIC ECM | Basic Setup | Design | Functional Specification |  |  | 3 | 4560
MIC ECM | Basic Setup | Installation & configuration on test & production environment | Setup of MIC ECM on test environment |  |  | 1 | 1360
MIC ECM | Basic Setup | Installation & configuration on test & production environment | Setup of MIC ECM on production environment |  |  | 0.5 | 680
MIC ECM | Basic Setup | Installation & configuration on test & production environment | Configuration of master data on test environment |  | Assumption 1 company/plant combination | 1 | 1360
MIC ECM | Basic Setup | Installation & configuration on test & production environment | Configuration of master data on production environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC ECM | Basic Setup | Installation & configuration on test & production environment | Setup of user and security settings on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC ECM | Basic Setup | Installation & configuration on test & production environment | Setup of user and security settings on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC ECM | Basic Setup | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC ECM | Basic Setup | Integration tests | Support during integration tests |  |  | 3 | 4080
MIC ECM | Basic Setup | Overall business process test on test & production environment | Definition of test cases |  |  | 2 | 2720
MIC ECM | Basic Setup | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 4 | 5440
MIC ECM | Basic Setup | Training and Go-Live Support | CWT (Client Walk Through) - MIC ECM - Key User |  | Assumption: not needed; covered with user training | 0 | 0
MIC ECM | Basic Setup | Training and Go-Live Support | Key User Training - MIC ECM |  | Assumption: on-site (0,5 out of 2 days are for preparation and wrap-up activities), 1 trip estimated | 2.5 | 3200 |  |  | 2 | days |  |  |  | 1
MIC ECM | Basic Setup | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC ECM - Key User |  | Assumption: 2 weeks 1 day per week | 2 | 2560 |  |  | 2 | weeks | 1 | day per week
MIC ECM | Basic Setup | Training and Go-Live Support | Go-Live Support - MIC ECM |  | Assumption: done remote; Remaining efforts are covered by business case rollout which is done for min. 1 business case in parallel | 1 | 1280
MIC ECM | Basic Setup | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC CCS ECC | Per Regime | Design | Process description for new regime |  |  | 1 | 1520
MIC CCS ECC | Per Regime | Installation & configuration on test & production environment | Configuration of master data MIC CCS ECC for regime on test environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC CCS ECC | Per Regime | Installation & configuration on test & production environment | Configuration of master data MIC CCS ECC for regime on production environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC CCS ECC | Per Regime | Installation & configuration on test & production environment | Setup of user and security settings for country on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC CCS ECC | Per Regime | Installation & configuration of interfaces on test- and production environment | Configuration of existing interface to upload data for commodity list |  | Assumption: Existing interfaces can be reused | 0.5 | 680
MIC CCS ECC | Per Regime | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC CCS ECC | Per Regime | Data migration |  |  | Assumption: data will be uploaded via interfaces (no manual migration required) | 0 | 0
MIC CCS ECC | Per Regime | Overall business process test on test & production environment | Definition of test cases |  |  | 0.5 | 680
MIC CCS ECC | Per Regime | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 1 | 1360
MIC CCS ECC | Per Regime | Training and Go-Live Support | CWT (Client Walk Through) - MIC CCS - Key User |  | Assumption: not needed; covered with user training | 0 | 0
MIC CCS ECC | Per Regime | Training and Go-Live Support | Key User Training - MIC CCS |  | Assumption: already inlcuded in basic setup efforts | 0 | 0
MIC CCS ECC | Per Regime | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC CCS Key User |  | Assumption: already inlcuded in basic setup efforts | 0 | 0
MIC CCS ECC | Per Regime | Training and Go-Live Support | Go-Live Support - MIC CCS ECC - Key User |  | Assumption: done remotely | 0.5 | 640
MIC CCS ECC | Per Regime | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC ECM | Per Regime | Design | Process description for new regime |  |  | 1 | 1520
MIC ECM | Per Regime | Installation & configuration on test & production environment | Configuration of master data MIC ECM for regime on test environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC ECM | Per Regime | Installation & configuration on test & production environment | Configuration of master data MIC ECM for regime on production environment |  | Assumption 1 company/plant combination | 0.25 | 340
MIC ECM | Per Regime | Installation & configuration on test & production environment | Setup of user and security settings for country on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC ECM | Per Regime | Installation & configuration on test & production environment | Setup of user and security settings for country on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC ECM | Per Regime | Installation & configuration of interfaces on test- and production environment | Configuration of existing interface to upload data for commodity list |  |  | 0.5 | 680
MIC ECM | Per Regime | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC ECM | Per Regime | Data migration | Upload of existing licenses |  |  | 1.5 | 2040
MIC ECM | Per Regime | Overall business process test on test & production environment | Definition of test cases |  |  | 0.5 | 680
MIC ECM | Per Regime | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 1 | 1360
MIC ECM | Per Regime | Training and Go-Live Support | CWT (Client Walk Through) - MIC ECM - Key User |  | Assumption: not needed; covered with user training | 0 | 0
MIC ECM | Per Regime | Training and Go-Live Support | Key User Training - MIC ECM |  | Assumption: not needed; covered with MIC ECM Basic Setup | 0 | 0
MIC ECM | Per Regime | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC ECM Key User |  | Assumption: already inlcuded in basic setup efforts | 0 | 0
MIC ECM | Per Regime | Training and Go-Live Support | Go-Live Support - MIC ECM |  | Assumption: done remotely | 1 | 1280
MIC ECM | Per Regime | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC ECM | Rollout per Location | Design | Workshop |  | 1 Workshop à 1 day to ensure that existing MIC processes can be rolled-out; 1 trip estimated | 1 | 1520 | 1 | workshop | 1 | day |  |  | 1
MIC ECM | Rollout per Location | Design | Update of existing process description |  |  | 0.5 | 760
MIC ECM | Rollout per Location | Installation & configuration on test & production environment | Setup of user and security settings on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC ECM | Rollout per Location | Installation & configuration on test & production environment | Setup of user and security settings on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC ECM | Rollout per Location | Installation & configuration of interfaces on test- and production environment | 1 interface from <company> to MIC CCS for new parts (analysis, documentation, scripts for upload & job scheduling, tests) via MIC Webservices |  | Assumption: Existing interfaces can be re-used for other locations without modification | 1 | 1360
MIC ECM | Rollout per Location | Installation & configuration of interfaces on test- and production environment | 1 interface from <company> to MIC ECM for shipment data (analysis, documentation, scripts for upload & job scheduling, tests) via MIC Webservices |  | Assumption: Existing interfaces can be re-used for other locations without modification | 1 | 1360
MIC ECM | Rollout per Location | Installation & configuration of interfaces on test- and production environment | 1 interface from MIC ECM to <company> for blocking of transactions (analysis, documentation, scripts for upload & job scheduling, tests) via MIC Webservices |  | Assumption: Existing interfaces can be re-used for other locations without modification | 1 | 1360
MIC ECM | Rollout per Location | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC ECM | Rollout per Location | Data migration |  |  | Assumption: not required | 0 | 0
MIC ECM | Rollout per Location | Overall business process test on test & production environment | Definition of test cases |  |  | 0.5 | 680
MIC ECM | Rollout per Location | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 1 | 1360
MIC ECM | Rollout per Location | Training and Go-Live Support | Training - MIC ECM - Key User |  | 0,5 out of 1 days are for preparation and wrap-up activities | 1 | 1280 |  |  | 1 | day
MIC ECM | Rollout per Location | Training and Go-Live Support | Go-Live Support - MIC ECM - remote |  |  | 1 | 1280
MIC ECM | Rollout per Location | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC OCS | Basic Setup | Design | Project Kick-Off Workshop |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 6 | 9120 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC OCS | Basic Setup | Design | Requirements Definition |  | Assumption: per remote | 2 | 3040
MIC OCS | Basic Setup | Design | Process Design & Description |  | incl. high-level project scope, project assumptions & dependencies | 2 | 3040
MIC OCS | Basic Setup | Design | Functional Specification |  | incl. company/plant setup, master data setup, user security | 1 | 1520
MIC OCS | Basic Setup | Installation & configuration on test & production environment | Setup of MIC OCS on test & production environment |  |  | 1 | 1360
MIC OCS | Basic Setup | Installation & configuration on test & production environment | Configuration of MIC OCS on test & production environment |  | Assumption: 1 company/plant combination | 1.5 | 2040
MIC OCS | Basic Setup | Installation & configuration on test & production environment | Setup of user and security settings on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC OCS | Basic Setup | Installation & configuration on test & production environment | Setup and configuration of Part Master Data |  | Assumption: considered in MIC CCS Basic Setup / MIC CCS Basic Setup Part Master | 0 | 0
MIC OCS | Basic Setup | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC OCS | Basic Setup | Integration tests |  |  | Efforts considered in MIC Interfaces | 0 | 0
MIC OCS | Basic Setup | Overall business process test on test & production environment |  |  | Efforts considered in OCS SCS, OCS CALC | 0 | 0
MIC OCS | Basic Setup | Data Migration | Migration of Part Master Data |  | Assumption: considered in MIC CCS Basic Setup / MIC CCS Basic Setup Part Master | 0 | 0
MIC OCS | Basic Setup | Data Migration | Migration of Business Partner Master Data |  | Assumption: Master Data will be provided in MIC specified CSV/XLS format | 1.5 | 2040
MIC OCS SCS | Supply Chain Solicitation | Design | Requirements Definition |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 6 | 9120 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC OCS SCS | Supply Chain Solicitation | Design | Process Design & Description |  | solicitation workflow/big picture, description of business process to system integration, request/response process to/from suppliers, etc. | 4 | 6080
MIC OCS SCS | Supply Chain Solicitation | Design | Functional Specification |  | specification of customizing, supplier portal definition and integration | 2 | 3040
MIC OCS SCS | Supply Chain Solicitation | Installation & configuration on test & production environment | Setup of MIC OCS SCS incl. Supplier portal (OCS Web) on test & production environment |  |  | 2.5 | 3400
MIC OCS SCS | Supply Chain Solicitation | Installation & configuration on test & production environment | Configuration of master data on test & production environment |  | Assumption 1 company/plant combination | 3 | 4080
MIC OCS SCS | Supply Chain Solicitation | Installation & configuration on test & production environment | Setup of user and security settings on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1.5 | 2040
MIC OCS SCS | Supply Chain Solicitation | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC OCS SCS | Supply Chain Solicitation | Data migration | Upload of existing supplier users |  |  | 1 | 1360
MIC OCS SCS | Supply Chain Solicitation | Data migration | Upload of supplier declaration requests |  |  | 1 | 1360
MIC OCS SCS | Supply Chain Solicitation | Data migration | Optional: Upload of existing supplier declarations |  |  | 2 | 2720
MIC OCS SCS | Supply Chain Solicitation | Data migration | Upload of existing supplier details |  | Assumption: considered in MIC OCS Basic Setup (Business Partner Master Data) | 0 | 0
MIC OCS SCS | Supply Chain Solicitation | Overall business process test on test & production environment | Definition of business process test cases |  | Assumption: based on business cases defined in process description | 2 | 2720
MIC OCS SCS | Supply Chain Solicitation | Overall business process test on test & production environment | Execution and analysis of defined business process tests |  |  | 3 | 4080
MIC OCS SCS | Supply Chain Solicitation | Training and Go-Live Support | CWT (Client Walk Through) - MIC OCS SCS - Key User |  | Assumption: remote (0,5 out of 1,0 days are for preparation and wrap-up activities) | 1 | 1280 |  |  | 1 | day
MIC OCS SCS | Supply Chain Solicitation | Training and Go-Live Support | Key User Training - MIC OCS SCS |  | Assumption: on-site (0,5 out of 1,5 days are for preparation and wrap-up activities), 1 trip estimated, MIC Standard User Guide will be used, Handout for Key-User Training will be provided | 1.5 | 1920 |  |  | 1.5 | days |  |  | 1
MIC OCS SCS | Supply Chain Solicitation | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC OCS SCS Key User |  | Assumption: 2 weeks 1 day per week | 2 | 2560 |  |  | 2 | weeks | 1 | day per week
MIC OCS SCS | Supply Chain Solicitation | Training and Go-Live Support | Go-Live Support MIC OCS SCS |  | Assumption: done remotely | 2 | 2560
MIC OCS SCS | Supply Chain Solicitation | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC OCS | Per FTA Bundle | Design | Requirements Definition to discuss FTA Bundle and RoO Setup |  | Assumptions: remote | 3 | 4560
MIC OCS | Per FTA Bundle | Design | Process Design & Description |  | Definition of FTA Bundle, Specification of RoO Setup | 2 | 3040
MIC OCS | Per FTA Bundle | Design | Functional Specification |  | Specification of customizing | 1 | 1520
MIC OCS | Per FTA Bundle | Installation & configuration on test & production environment | Upload & configuration per FTA Bundle on test & production environment |  | Assumption: 0,75 days per FTA incl. 1,5 days per Bundle ¦ in scope: <#> EU FTAs | 9 | 12240 |  |  | 9 | days
MIC OCS | Per FTA Bundle | Installation & configuration on test & production environment | Setup of Rules of Origin per FTA Bundle |  | Assumption: 1,25 days per different FTA RoO protocol ¦ in scope: 1 EU bundels, 10 different RoO protocols ¦ 40 different HS Positions | 12.5 | 17000 |  |  | 12.5 | days
MIC OCS | Per FTA Bundle | Installation & configuration on test & production environment | Update of user and security settings on test & production environment |  | Update on existing security settings - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC OCS | Per FTA Bundle | Installation & configuration of interfaces on test- and production environment | Configuration of 2 existing interfaces (see basic activities regarding OCS) for FTA |  |  | 1 | 1360
MIC OCS | Per FTA Bundle | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC OCS | Per FTA Bundle | Data migration |  |  | not needed | 0 | 0
MIC OCS | Per FTA Bundle | Overall business process test on test & production environment | Definition of FTA / Bundle specific test cases |  | Assumption: based on FTA setup and usage defined in process description | 1 | 1360
MIC OCS | Per FTA Bundle | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 1.5 | 2040
MIC OCS | Per FTA Bundle | Training and Go-Live Support | CWT (Client Walk Through) - MIC OCS - Key User |  | Assumption: walkthrough of FTA / Bundle setup; done remote (0,5 out of 1,0 days are for preparation and wrap-up activities) | 1 | 1280 |  |  | 1 | day
MIC OCS | Per FTA Bundle | Training and Go-Live Support | Key User Training - MIC OCS |  | Assumption: no FTA / Bundle specfic training needed | 0 | 0
MIC OCS | Per FTA Bundle | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC OCS SCS + CALC Key User |  | Assumption: 2 days per FTA Bundle | 2 | 2560 |  |  | 2 | days
MIC OCS | Per FTA Bundle | Training and Go-Live Support | Go-Live Support MIC OCS SCS + CALC |  | Assumption: done remote; 2 days per FTA Bundle | 2 | 2560 |  |  | 2 | days
MIC OCS | Per FTA Bundle | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC OCS | Per FTA | Design | Requirements Definition to discuss FTA and RoO Setup |  | Assumptions: remote | 1.5 | 2280
MIC OCS | Per FTA | Design | Process Design & Description |  | Definition of FTA specific processes, Specification of RoO Setup | 1 | 1520
MIC OCS | Per FTA | Design | Functional Specification |  | Specification of FTA specific customizing | 1 | 1520
MIC OCS | Per FTA | Installation & configuration on test & production environment | Upload & configuration of FTA on test & production environment |  | Assumption: 1,5 days per FTA | 1.5 | 2040 |  |  | 1.5 | days
MIC OCS | Per FTA | Installation & configuration on test & production environment | Setup of Rules of Origin per FTA Bundle |  | Assumption: up to 50 different HS Postions | 1.5 | 2040
MIC OCS | Per FTA | Installation & configuration on test & production environment | Update of user and security settings on test & production environment |  | Update on existing security settings - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC OCS | Per FTA | Installation & configuration of interfaces on test- and production environment | Configuration of 2 existing interfaces (see basic activities regarding OCS) for FTA |  | Assumption: covered already | 0 | 0
MIC OCS | Per FTA | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC OCS | Per FTA | Data migration |  |  | not needed | 0 | 0
MIC OCS | Per FTA | Overall business process test on test & production environment | Definition of FTA specific test cases |  | Assumption: based on FTA setup and usage defined in process description | 0.5 | 680
MIC OCS | Per FTA | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 1 | 1360
MIC OCS | Per FTA | Training and Go-Live Support | CWT (Client Walk Through) - MIC OCS - Key Use |  | Assumption: walkthrough of FTA setup; done remote (0,5 out of 1,0 days are for preparation and wrap-up activities) | 1 | 1280 |  |  | 1 | day
MIC OCS | Per FTA | Training and Go-Live Support | Key User Training - MIC OCS |  | Assumption: no FTA specfic training needed | 0 | 0
MIC OCS | Per FTA | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC OCS SCS + CALC Key User |  | Assumption: 1 MD per FTA | 1 | 1280 |  |  | 1 | day
MIC OCS | Per FTA | Training and Go-Live Support | Go-Live Support MIC OCS SCS + CALC |  | Assumption: done remote; 1 MD per FTA | 1 | 1280 |  |  | 1 | day
MIC OCS | Per FTA | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC OCS | Rollout per Region | Design | Requirements Definition |  | Assumptions: 2 Sessions with 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 12 | 18240 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC OCS | Rollout per Region | Design | Process Design & Description |  | solicitation and calculation workflow/big picture, description of region specific business process deviations compared to inital definied processes | 5 | 7600
MIC OCS | Rollout per Region | Design | Functional Specification |  | specification of region specific customizing | 3 | 4560
MIC OCS | Rollout per Region | Installation & configuration on test & production environment | Setup of new Company/Plant for MIC OCS SCS and MIC OCS CALC on test & production environment |  |  | 1.5 | 2040
MIC OCS | Rollout per Region | Installation & configuration on test & production environment | Configuration of master data on test & production environment |  | Assumption 1 company/plant combination | 3 | 4080
MIC OCS | Rollout per Region | Installation & configuration on test & production environment | Setup of user and security settings on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1.5 | 2040
MIC OCS | Rollout per Region | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC ALL / MIC OCS SCS (see "MIC Interfaces") concerning the loading of users using Supplier Portal (MIC OCS Web) |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Region | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC ALL (see "MIC Interfaces") concerning the loading Business Partner Data |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Region | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC CCS (see "MIC Interfaces") concerning the loading of part master data |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Region | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-OCS (see "MIC Interfaces") concerning the loading of Origin Calculation and/or Supplier Declaration Results |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Region | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-OCS SCS (see "MIC Interfaces") concerning the loading of new Supplier Declaration Requests |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Region | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC OCS CALC (see "MIC Interfaces") concerning the loading of Bill Of Materials (BOM) |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Region | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC OCS CALC (see "MIC Interfaces") concerning the triggering of Origin Calculation |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Region | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC OCS CALC (see "MIC Interfaces") concerning the requesting of customer supplier declarations |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Region | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC OCS | Rollout per Region | Data migration | Upload of existing supplier users |  |  | 1 | 1360
MIC OCS | Rollout per Region | Data migration | Upload of supplier declaration requests |  |  | 1 | 1360
MIC OCS | Rollout per Region | Data migration | Optional: Upload of existing supplier declarations |  |  | 2 | 2720
MIC OCS | Rollout per Region | Data migration | Upload of existing supplier details |  | Assumption: considered in MIC OCS Basic Setup | 1 | 1360
MIC OCS | Rollout per Region | Data migration | Upload of existing BOMs |  |  | 1 | 1360
MIC OCS | Rollout per Region | Data migration | Optional: Upload of additional part prices |  |  | 1 | 1360
MIC OCS | Rollout per Region | Data migration | Upload of existing client details |  | Assumption: considered in MIC OCS Basic Setup | 1 | 1360
MIC OCS | Rollout per Region | Overall business process test on test & production environment | Definition of business process test cases |  | Assumption: based on business cases defined in process description | 3 | 4080
MIC OCS | Rollout per Region | Overall business process test on test & production environment | Execution and analysis of defined business process tests |  |  | 4 | 5440
MIC OCS | Rollout per Region | Training and Go-Live Support | CWT (Client Walk Through) - MIC OCS - Key User |  | Assumption: remote (0,5 out of 1,0 days are for preparation and wrap-up activities) | 1 | 1280 |  |  | 1 | day
MIC OCS | Rollout per Region | Training and Go-Live Support | Key User Training - MIC OCS |  | Assumption: on-site (0,5 out of 2,0 days are for preparation and wrap-up activities) ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 2 | 2560 |  |  | 2 | days |  |  |  | 1
MIC OCS | Rollout per Region | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC OCS Key User |  | Assumption: 2 weeks 1,5 day per week | 3 | 3840 |  |  | 2 | weeks | 1.5 | days per week
MIC OCS | Rollout per Region | Training and Go-Live Support | Go-Live Support MIC OCS |  | Assumption: done remotely | 4 | 5120
MIC OCS | Rollout per Region | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC OCS CALC | Origin Calculation | Design | Requirements Definition |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 6 | 9120 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC OCS CALC | Origin Calculation | Design | Process Design & Description |  | calculation workflow/big picture, description of business process to system integration, calculation request/result process, etc. | 4 | 6080
MIC OCS CALC | Origin Calculation | Design | Functional Specification |  | specification of customizing | 1 | 1520
MIC OCS CALC | Origin Calculation | Installation & configuration on test & production environment | Setup of MIC OCS CALC on test & production environment |  |  | 2.5 | 3400
MIC OCS CALC | Origin Calculation | Installation & configuration on test & production environment | Configuration of master data on test & production environment |  | Assumption 1 company/plant combination | 3 | 4080
MIC OCS CALC | Origin Calculation | Installation & configuration on test & production environment | Setup of user and security settings on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1.5 | 2040
MIC OCS CALC | Origin Calculation | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC OCS CALC | Origin Calculation | Data migration | Upload of existing BOMs |  |  | 1 | 1360
MIC OCS CALC | Origin Calculation | Data migration | Optional: Upload of additional part prices |  |  | 1 | 1360
MIC OCS CALC | Origin Calculation | Data migration | Upload of existing client details |  | Assumption: considered in MIC OCS Basic Setup (Business Partner Master Data) | 0 | 0
MIC OCS CALC | Origin Calculation | Overall business process test on test & production environment | Definition of business process test cases |  | Assumption: based on business cases defined in process description | 2 | 2720
MIC OCS CALC | Origin Calculation | Overall business process test on test & production environment | Execution and analysis of defined business process tests |  |  | 3 | 4080
MIC OCS CALC | Origin Calculation | Training and Go-Live Support | CWT (Client Walk Through) - MIC OCS CALC - Key User |  | Assumption: remote (0,5 out of 1,0 days are for preparation and wrap-up activities) | 1 | 1280 |  |  | 1 | day
MIC OCS CALC | Origin Calculation | Training and Go-Live Support | Key User Training - MIC OCS CALC |  | Assumption: on-site (0,5 out of 1,5 days are for preparation and wrap-up activities) ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 1.5 | 1920 |  |  | 1.5 | days |  |  | 1
MIC OCS CALC | Origin Calculation | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC OCS CALC Key User |  | Assumption: 2 weeks 1 day per week | 2 | 2560 |  |  | 2 | weeks | 1 | day per week
MIC OCS CALC | Origin Calculation | Training and Go-Live Support | Go-Live Support MIC OCS CALC |  | Assumption: done remotely | 2 | 2560
MIC OCS CALC | Origin Calculation | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC OCS | Rollout per Location | Design | Requirements Definition |  | Assumptions: 1 Sessions with 2 experts, 1 days workshop on-site, 1 days preparation & wrap-up | 3 | 4560 | 1 | workshop | 1 | day | 2 | MIC expert(s)
MIC OCS | Rollout per Location | Design | Process Design & Description |  | solicitation and calculation workflow/big picture, description of location specific business process deviations compared to inital definied processes | 2 | 3040
MIC OCS | Rollout per Location | Design | Functional Specification |  | specification of location specific customizing | 1 | 1520
MIC OCS | Rollout per Location | Installation & configuration on test & production environment | Setup of new Company/Plant for MIC OCS SCS and MIC OCS CALC on test & production environment |  |  | 1.5 | 2040
MIC OCS | Rollout per Location | Installation & configuration on test & production environment | Configuration of master data on test & production environment |  | Assumption 1 company/plant combination | 3 | 4080
MIC OCS | Rollout per Location | Installation & configuration on test & production environment | Setup of user and security settings on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC OCS | Rollout per Location | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC ALL (see "MIC Interfaces") concerning the loading Business Partner Data |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Location | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC CCS (see "MIC Interfaces") concerning the loading of part master data |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Location | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-OCS (see "MIC Interfaces") concerning the loading of Origin Calculation and/or Supplier Declaration Results |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Location | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-OCS SCS (see "MIC Interfaces") concerning the loading of new Supplier Declaration Requests |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Location | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC ALL / MIC OCS SCS (see "MIC Interfaces") concerning the loading of users using Supplier Portal (MIC OCS Web) |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Location | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC OCS CALC (see "MIC Interfaces") concerning the loading of Bill Of Materials (BOM) |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Location | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC OCS CALC (see "MIC Interfaces") concerning the triggering of Origin Calculation |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Location | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC OCS CALC (see "MIC Interfaces") concerning the requesting of customer supplier declarations |  | Assumption: Existing interfaces from same ERP can be re-used without modification | 1 | 1360
MIC OCS | Rollout per Location | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC OCS | Rollout per Location | Data migration | Upload of existing supplier users |  |  | 0.5 | 680
MIC OCS | Rollout per Location | Data migration | Upload of supplier declaration requests |  |  | 0.5 | 680
MIC OCS | Rollout per Location | Data migration | Optional: Upload of existing supplier declarations |  |  | 1 | 1360
MIC OCS | Rollout per Location | Data migration | Upload of existing supplier details |  | Assumption: considered in MIC OCS Basic Setup | 0.5 | 680
MIC OCS | Rollout per Location | Data migration | Upload of existing BOMs |  |  | 0.5 | 680
MIC OCS | Rollout per Location | Data migration | Optional: Upload of additional part prices |  |  | 0.5 | 680
MIC OCS | Rollout per Location | Data migration | Upload of existing client details |  | Assumption: considered in MIC OCS Basic Setup | 0.5 | 680
MIC OCS | Rollout per Location | Overall business process test on test & production environment | Definition of business process test cases |  | Assumption: based on business cases defined in process description | 1 | 1360
MIC OCS | Rollout per Location | Overall business process test on test & production environment | Execution and analysis of defined business process tests |  |  | 2 | 2720
MIC OCS | Rollout per Location | Training and Go-Live Support | CWT (Client Walk Through) - MIC OCS - Key User |  | Assumption: new users are added for localtion; done remote (0,5 out of 1,0 days are for preparation and wrap-up activities) | 1 | 1280 |  |  | 1 | day
MIC OCS | Rollout per Location | Training and Go-Live Support | Key User Training - MIC OCS |  | Assumption: on-site (0,5 out of 1,5 days are for preparation and wrap-up activities) ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 1.5 | 1920 |  |  | 1.5 | days |  |  | 1
MIC OCS | Rollout per Location | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC OCS Key User |  | Assumption: 2 weeks 1,0 day per week | 2 | 2560 |  |  | 2 | weeks | 1 day per week
MIC OCS | Rollout per Location | Training and Go-Live Support | Go-Live Support MIC OCS |  | Assumption: done remotely | 2 | 2560
MIC OCS | Rollout per Location | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC-CUST | Basic Setup | Design | Project Kick-Off Workshop |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 6 | 9120 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC-CUST | Basic Setup | Design | Requirements Definition |  | Assumption: per remote | 2 | 3040
MIC-CUST | Basic Setup | Design | Process Design & Description |  | incl. high-level project scope, project assumptions & dependencies | 2 | 3040
MIC-CUST | Basic Setup | Design | Functional Specification |  | incl. company/plant setup, master data setup, user security | 1 | 1520
MIC-CUST | Basic Setup | Installation & configuration on test & production environment | Setup of MIC CUST on test & production environment |  |  | 1 | 1360
MIC-CUST | Basic Setup | Installation & configuration on test & production environment | Configuration of MIC CUST on test & production environment |  | Assumption: 1 company/plant combination | 1.5 | 2040
MIC-CUST | Basic Setup | Installation & configuration on test & production environment | Setup of user and security settings on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC-CUST | Basic Setup | Installation & configuration on test & production environment | Configuration of MIC-GTCS for global trade content services |  | currency exchange rates | 0.5 | 680
MIC-CUST | Basic Setup | Installation & configuration on test & production environment | Setup and configuration of Part Master Data |  | Assumption: considered in MIC CCS Basic Setup / MIC CCS Basic Setup Part Master | 0 | 0
MIC-CUST | Basic Setup | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST | Basic Setup | Integration tests |  |  | Efforts considered in MIC Interfaces | 0 | 0
MIC-CUST | Basic Setup | Overall business process test on test & production environment |  |  | Efforts considered in Import, Export, Stocks | 0 | 0
MIC-CUST | Basic Setup | Data Migration | Migration of Part Master Data |  | Assumption: considered in MIC CCS Basic Setup / MIC CCS Basic Setup Part Master | 0 | 0
MIC-CUST | Basic Setup | Data Migration | Migration of Business Partner Master Data |  | Assumption: Master Data will be provided in MIC specified CSV/XLS format | 1.5 | 2040
MIC-CUST Import | per Country | Design | Requirements Definition |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 6 | 9120 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC-CUST Import | per Country | Design | Process Design & Description (MIC-CUST) |  | high-level project scope, project assumptions & dependencies, workflow/big picture, description of processes per business case incl. system integration, filing process to/from authorities, supplements, etc. | 3 | 4560
MIC-CUST Import | per Country | Design | Functional Specification (MIC-CUST) |  | company/plant structure, specification of customizing, definition and/or specification of reports, defaulting, etc. | 2 | 3040
MIC-CUST Import | per Country | Design | Process Design & Description (MIC-NCTS) |  | project assumptions & dependencies, description of processes, filing process to/from authorities | 1 | 1520
MIC-CUST Import | per Country | Installation & configuration on test & production environment | Installation of country specific patch |  |  | 1 | 1360
MIC-CUST Import | per Country | Installation & configuration on test & production environment | Configuration of MIC-CUST® Import on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 2 | 2720
MIC-CUST Import | per Country | Installation & configuration on test & production environment | Configuration of MIC NCTS CE on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 0.5 | 680
MIC-CUST Import | per Country | Installation & configuration on test & production environment | Setup of user and security settings for country on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC-CUST Import | per Country | Installation & configuration on test & production environment | Configuration of MIC-GTCS for global trade content services |  | dynamic list of values for DE | 0.5 | 680
MIC-CUST Import | per Country | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 0.5 | 680
MIC-CUST Import | per Country | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated Integration Tests of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 1 | 1360
MIC-CUST Import | per Country | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST Import | per Country | Authority communication | Setup of authority communication for MIC-CUST Import (for SaaS solution) |  |  | 1 | 1360
MIC-CUST Import | per Country | Authority communication | Support at the setup of authority communication for MIC-CUST Import (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 2 | 2720
MIC-CUST Import | per Country | Authority communication | Creating and sending of test messages for MIC-CUST Import to the authorities |  | valid for SaaS and On-Premises solution | 1 | 1360
MIC-CUST Import | per Country | Authority communication | Setup of authority communication for MIC-NCTS CE (for SaaS solution) |  |  | 0.5 | 680
MIC-CUST Import | per Country | Authority communication | Support at the setup of authority communication for MIC-NCTS CE (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 1 | 1360
MIC-CUST Import | per Country | Authority communication | Creating and sending of test messages for MIC-NCTS CE to the authorities |  | valid for SaaS and On-Premises solution | 0.5 | 680
MIC-CUST Import | per Country | Data migration | Migration of part data |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | per Country | Data migration | Migration of addresses |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | per Country | Overall business process test on test & production environment | Definition of business process test cases (MIC-CUST Import) |  | Assumption: based on business cases defined in process description | 1 | 1360
MIC-CUST Import | per Country | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-CUST Import) |  |  | 3 | 4080
MIC-CUST Import | per Country | Overall business process test on test & production environment | Definition of business process test cases (MIC-NCTS CE) |  | Assumption: based on business cases defined in process description | 0.5 | 680
MIC-CUST Import | per Country | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-NCTS CE) |  |  | 1 | 1360
MIC-CUST Import | per Country | Training and Go-Live Support | CWT (Client Walk Through) |  | Assumption: not needed; covered with user training | 0 | 0
MIC-CUST Import | per Country | Training and Go-Live Support | Key User Training - MIC-CUST® Import |  | 1,5 out of 2,5 days are for preparation and wrap-up activities ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 2.5 | 3200 |  |  | 2.5 | days |  |  | 1
MIC-CUST Import | per Country | Training and Go-Live Support | Support at UAT (User Acceptance Test) |  | Assumption: 3 weeks, 1 day per week | 3 | 3840 |  |  | 3 | weeks | 1 | day per week
MIC-CUST Import | per Country | Training and Go-Live Support | Go-Live Support |  | 1 trip estimated | 3 | 3840 | [8 empty] | 1
MIC-CUST Import | per Country | Training and Go-Live Support | Service Transition |  |  | 1 | 1280
MIC-CUST Import | DE | Design | Requirements Definition |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 6 | 9120 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC-CUST Import | DE | Design | Process Design & Description (MIC-CUST) |  | high-level project scope, project assumptions & dependencies, workflow/big picture, description of processes per business case incl. system integration, filing process to/from authorities, supplements, etc. | 3 | 4560
MIC-CUST Import | DE | Design | Functional Specification (MIC-CUST) |  | company/plant structure, specification of customizing, definition and/or specification of reports, defaulting, etc. | 2 | 3040
MIC-CUST Import | DE | Design | Process Design & Description (MIC-NCTS) |  | project assumptions & dependencies, description of processes, filing process to/from authorities | 1 | 1520
MIC-CUST Import | DE | Installation & configuration on test & production environment | Installation of country specific patch |  |  | 1 | 1360
MIC-CUST Import | DE | Installation & configuration on test & production environment | Configuration of MIC-CUST® Import on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 2 | 2720
MIC-CUST Import | DE | Installation & configuration on test & production environment | Configuration of MIC NCTS CE on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 0.5 | 680
MIC-CUST Import | DE | Installation & configuration on test & production environment | Setup of user and security settings for country on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC-CUST Import | DE | Installation & configuration on test & production environment | Configuration of MIC-GTCS for global trade content services |  | dynamic list of values for DE | 0.5 | 680
MIC-CUST Import | DE | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 0.5 | 680
MIC-CUST Import | DE | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated Integration Tests of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 1 | 1360
MIC-CUST Import | DE | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST Import | DE | Authority communication | Setup of authority communication for MIC-CUST Import (for SaaS solution) |  |  | 1 | 1360
MIC-CUST Import | DE | Authority communication | Support at the setup of authority communication for MIC-CUST Import (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 2 | 2720
MIC-CUST Import | DE | Authority communication | Creating and sending of test messages for MIC-CUST Import to the authorities |  | valid for SaaS and On-Premises solution | 1 | 1360
MIC-CUST Import | DE | Authority communication | Setup of authority communication for MIC-NCTS CE (for SaaS solution) |  |  | 0.5 | 680
MIC-CUST Import | DE | Authority communication | Support at the setup of authority communication for MIC-NCTS CE (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 1 | 1360
MIC-CUST Import | DE | Authority communication | Creating and sending of test messages for MIC-NCTS CE to the authorities |  | valid for SaaS and On-Premises solution | 0.5 | 680
MIC-CUST Import | DE | Data migration | Migration of part data |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | DE | Data migration | Migration of addresses |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | DE | Overall business process test on test & production environment | Definition of business process test cases (MIC-CUST Import) |  | Assumption: based on business cases defined in process description | 1 | 1360
MIC-CUST Import | DE | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-CUST Import) |  |  | 3 | 4080
MIC-CUST Import | DE | Overall business process test on test & production environment | Definition of business process test cases (MIC-NCTS CE) |  | Assumption: based on business cases defined in process description | 0.5 | 680
MIC-CUST Import | DE | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-NCTS CE) |  |  | 1 | 1360
MIC-CUST Import | DE | Training and Go-Live Support | CWT (Client Walk Through) |  | Assumption: not needed; covered with user training | 0 | 0
MIC-CUST Import | DE | Training and Go-Live Support | Key User Training - MIC-CUST® Import |  | 1,5 out of 2,5 days are for preparation and wrap-up activities ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 2.5 | 3200 |  |  | 2.5 | days |  |  | 1
MIC-CUST Import | DE | Training and Go-Live Support | Support at UAT (User Acceptance Test) |  | Assumption: 3 weeks, 1 day per week | 3 | 3840 |  |  | 3 | weeks | 1 | day per week
MIC-CUST Import | DE | Training and Go-Live Support | Go-Live Support |  | 1 trip estimated | 3 | 3840 | [8 empty] | 1
MIC-CUST Import | DE | Training and Go-Live Support | Service Transition |  |  | 1 | 1280
MIC-CUST Import | HU | Design | Requirements Definition |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 6 | 9120 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC-CUST Import | HU | Design | Process Design & Description (MIC-CUST) |  | high-level project scope, project assumptions & dependencies, workflow/big picture, description of processes per business case incl. system integration, filing process to/from authorities, supplements, etc. | 2 | 3040
MIC-CUST Import | HU | Design | Functional Specification (MIC-CUST) |  | company/plant structure, specification of customizing, definition and/or specification of reports, defaulting, etc. | 2 | 3040
MIC-CUST Import | HU | Design | Process Design & Description (MIC-NCTS) |  | project assumptions & dependencies, description of processes, filing process to/from authorities | 1 | 1520
MIC-CUST Import | HU | Installation & configuration on test & production environment | Installation of country specific patch |  |  | 1 | 1360
MIC-CUST Import | HU | Installation & configuration on test & production environment | Configuration of MIC-CUST® Import on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 2.5 | 3400
MIC-CUST Import | HU | Installation & configuration on test & production environment | Configuration of MIC NCTS CE on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 0.5 | 680
MIC-CUST Import | HU | Installation & configuration on test & production environment | Setup of user and security settings for country on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC-CUST Import | HU | Installation & configuration on test & production environment | Configuration of MIC-GTCS for global trade content services |  | dynamic list of values for DE |  | 0
MIC-CUST Import | HU | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 0.5 | 680
MIC-CUST Import | HU | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated Integration Tests of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 1 | 1360
MIC-CUST Import | HU | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST Import | HU | Authority communication | Setup of authority communication for MIC-CUST Import (for SaaS solution) |  |  | 2 | 2720
MIC-CUST Import | HU | Authority communication | Support at the setup of authority communication for MIC-CUST Import (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 3 | 4080
MIC-CUST Import | HU | Authority communication | Creating and sending of test messages for MIC-CUST Import to the authorities |  | valid for SaaS and On-Premises solution | 1.5 | 2040
MIC-CUST Import | HU | Authority communication | Setup of authority communication for MIC-NCTS CE (for SaaS solution) |  |  | 2 | 2720
MIC-CUST Import | HU | Authority communication | Support at the setup of authority communication for MIC-NCTS CE (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 1.5 | 2040
MIC-CUST Import | HU | Authority communication | Creating and sending of test messages for MIC-NCTS CE to the authorities |  | valid for SaaS and On-Premises solution | 1 | 1360
MIC-CUST Import | HU | Data migration | Migration of part data |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | HU | Data migration | Migration of addresses |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | HU | Overall business process test on test & production environment | Definition of business process test cases (MIC-CUST Import) |  | Assumption: based on business cases defined in process description | 1 | 1360
MIC-CUST Import | HU | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-CUST Import) |  |  | 3 | 4080
MIC-CUST Import | HU | Overall business process test on test & production environment | Definition of business process test cases (MIC-NCTS CE) |  | Assumption: based on business cases defined in process description | 0.5 | 680
MIC-CUST Import | HU | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-NCTS CE) |  |  | 2 | 2720
MIC-CUST Import | HU | Training and Go-Live Support | CWT (Client Walk Through) |  | Assumption: not needed; covered with user training | 0 | 0
MIC-CUST Import | HU | Training and Go-Live Support | Key User Training - MIC-CUST® Import |  | 1,5 out of 2,5 days are for preparation and wrap-up activities ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 2.5 | 3200 |  |  | 2.5 | days |  |  | 1
MIC-CUST Import | HU | Training and Go-Live Support | Support at UAT (User Acceptance Test) |  | Assumption: 3 weeks, 1 day per week | 3 | 3840 |  |  | 3 | weeks | 1 | day per week
MIC-CUST Import | HU | Training and Go-Live Support | Go-Live Support |  | 1 trip estimated | 3 | 3840 | [8 empty] | 1
MIC-CUST Import | HU | Training and Go-Live Support | Service Transition |  |  | 1 | 1280
MIC-CUST Import | BE | Design | Requirements Definition |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 6 | 9120 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC-CUST Import | BE | Design | Process Design & Description (MIC-CUST) |  | high-level project scope, project assumptions & dependencies, workflow/big picture, description of processes per business case incl. system integration, filing process to/from authorities, supplements, etc. | 2 | 3040
MIC-CUST Import | BE | Design | Functional Specification (MIC-CUST) |  | company/plant structure, specification of customizing, definition and/or specification of reports, defaulting, etc. | 2 | 3040
MIC-CUST Import | BE | Design | Process Design & Description (MIC-NCTS) |  | project assumptions & dependencies, description of processes, filing process to/from authorities | 1 | 1520
MIC-CUST Import | BE | Installation & configuration on test & production environment | Installation of country specific patch |  |  | 1 | 1360
MIC-CUST Import | BE | Installation & configuration on test & production environment | Configuration of MIC-CUST® Import on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 2.5 | 3400
MIC-CUST Import | BE | Installation & configuration on test & production environment | Configuration of MIC NCTS CE on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 0.5 | 680
MIC-CUST Import | BE | Installation & configuration on test & production environment | Setup of user and security settings for country on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC-CUST Import | BE | Installation & configuration on test & production environment | Configuration of MIC-GTCS for global trade content services |  | dynamic list of values for DE |  | 0
MIC-CUST Import | BE | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 0.5 | 680
MIC-CUST Import | BE | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated Integration Tests of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 1 | 1360
MIC-CUST Import | BE | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST Import | BE | Authority communication | Setup of authority communication for MIC-CUST Import (for SaaS solution) |  |  | 2 | 2720
MIC-CUST Import | BE | Authority communication | Support at the setup of authority communication for MIC-CUST Import (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 3 | 4080
MIC-CUST Import | BE | Authority communication | Creating and sending of test messages for MIC-CUST Import to the authorities |  | valid for SaaS and On-Premises solution | 1.5 | 2040
MIC-CUST Import | BE | Authority communication | Setup of authority communication for MIC-NCTS CE (for SaaS solution) |  |  | 2 | 2720
MIC-CUST Import | BE | Authority communication | Support at the setup of authority communication for MIC-NCTS CE (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 1.5 | 2040
MIC-CUST Import | BE | Authority communication | Creating and sending of test messages for MIC-NCTS CE to the authorities |  | valid for SaaS and On-Premises solution | 1 | 1360
MIC-CUST Import | BE | Data migration | Migration of part data |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | BE | Data migration | Migration of addresses |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | BE | Overall business process test on test & production environment | Definition of business process test cases (MIC-CUST Import) |  | Assumption: based on business cases defined in process description | 1 | 1360
MIC-CUST Import | BE | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-CUST Import) |  |  | 3 | 4080
MIC-CUST Import | BE | Overall business process test on test & production environment | Definition of business process test cases (MIC-NCTS CE) |  | Assumption: based on business cases defined in process description | 0.5 | 680
MIC-CUST Import | BE | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-NCTS CE) |  |  | 2 | 2720
MIC-CUST Import | BE | Training and Go-Live Support | CWT (Client Walk Through) |  | Assumption: not needed; covered with user training | 0 | 0
MIC-CUST Import | BE | Training and Go-Live Support | Key User Training - MIC-CUST® Import |  | 1,5 out of 2,5 days are for preparation and wrap-up activities ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 2.5 | 3200 |  |  | 2.5 | days |  |  | 1
MIC-CUST Import | BE | Training and Go-Live Support | Support at UAT (User Acceptance Test) |  | Assumption: 3 weeks, 1 day per week | 3 | 3840 |  |  | 3 | weeks | 1 | day per week
MIC-CUST Import | BE | Training and Go-Live Support | Go-Live Support |  | 1 trip estimated | 3 | 3840 | [8 empty] | 1
MIC-CUST Import | BE | Training and Go-Live Support | Service Transition |  |  | 1 | 1280
MIC-CUST Import | NL | Design | Requirements Definition |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 3 | 4560 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC-CUST Import | NL | Design | Process Design & Description (MIC-CUST) |  | high-level project scope, project assumptions & dependencies, workflow/big picture, description of processes per business case incl. system integration, filing process to/from authorities, supplements, etc. | 2 | 3040
MIC-CUST Import | NL | Design | Functional Specification (MIC-CUST) |  | company/plant structure, specification of customizing, definition and/or specification of reports, defaulting, etc. | 1 | 1520
MIC-CUST Import | NL | Design | Process Design & Description (MIC-NCTS) |  | project assumptions & dependencies, description of processes, filing process to/from authorities | 1 | 1520
MIC-CUST Import | NL | Installation & configuration on test & production environment | Installation of country specific patch |  |  | 1 | 1360
MIC-CUST Import | NL | Installation & configuration on test & production environment | Configuration of MIC-CUST® Import on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 2.5 | 3400
MIC-CUST Import | NL | Installation & configuration on test & production environment | Configuration of MIC NCTS CE on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 0.5 | 680
MIC-CUST Import | NL | Installation & configuration on test & production environment | Setup of user and security settings for country on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC-CUST Import | NL | Installation & configuration on test & production environment | Configuration of MIC-GTCS for global trade content services |  | dynamic list of values for DE |  | 0
MIC-CUST Import | NL | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 0.5 | 680
MIC-CUST Import | NL | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated Integration Tests of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 1 | 1360
MIC-CUST Import | NL | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST Import | NL | Authority communication | Setup of authority communication for MIC-CUST Import (for SaaS solution) |  |  | 2 | 2720
MIC-CUST Import | NL | Authority communication | Support at the setup of authority communication for MIC-CUST Import (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 3 | 4080
MIC-CUST Import | NL | Authority communication | Creating and sending of test messages for MIC-CUST Import to the authorities |  | valid for SaaS and On-Premises solution | 1.5 | 2040
MIC-CUST Import | NL | Authority communication | Setup of authority communication for MIC-NCTS CE (for SaaS solution) |  |  | 2 | 2720
MIC-CUST Import | NL | Authority communication | Support at the setup of authority communication for MIC-NCTS CE (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 1.5 | 2040
MIC-CUST Import | NL | Authority communication | Creating and sending of test messages for MIC-NCTS CE to the authorities |  | valid for SaaS and On-Premises solution | 1 | 1360
MIC-CUST Import | NL | Data migration | Migration of part data |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | NL | Data migration | Migration of addresses |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | NL | Overall business process test on test & production environment | Definition of business process test cases (MIC-CUST Import) |  | Assumption: based on business cases defined in process description | 1 | 1360
MIC-CUST Import | NL | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-CUST Import) |  |  | 3 | 4080
MIC-CUST Import | NL | Overall business process test on test & production environment | Definition of business process test cases (MIC-NCTS CE) |  | Assumption: based on business cases defined in process description | 0.5 | 680
MIC-CUST Import | NL | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-NCTS CE) |  |  | 2 | 2720
MIC-CUST Import | NL | Training and Go-Live Support | CWT (Client Walk Through) |  | Assumption: not needed; covered with user training | 0 | 0
MIC-CUST Import | NL | Training and Go-Live Support | Key User Training - MIC-CUST® Import |  | 1,5 out of 2,5 days are for preparation and wrap-up activities ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 2.5 | 3200 |  |  | 2.5 | days |  |  | 1
MIC-CUST Import | NL | Training and Go-Live Support | Support at UAT (User Acceptance Test) |  | Assumption: 3 weeks, 1 day per week | 3 | 3840 |  |  | 3 | weeks | 1 | day per week
MIC-CUST Import | NL | Training and Go-Live Support | Go-Live Support |  | 1 trip estimated | 3 | 3840 | [8 empty] | 1
MIC-CUST Import | NL | Training and Go-Live Support | Service Transition |  |  | 2 | 2560
MIC-CUST Import | US | Design | Requirements Definition |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 4 | 6080 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC-CUST Import | US | Design | Process Design & Description (MIC-CUST) |  | high-level project scope, project assumptions & dependencies, workflow/big picture, description of processes per business case incl. system integration, filing process to/from authorities, supplements, etc. | 3 | 4560
MIC-CUST Import | US | Design | Functional Specification (MIC-CUST) |  | company/plant structure, specification of customizing, definition and/or specification of reports, defaulting, etc. | 1 | 1520
MIC-CUST Import | US | Design | Process Design & Description (MIC-NCTS) |  | project assumptions & dependencies, description of processes, filing process to/from authorities | 3 | 4560
MIC-CUST Import | US | Installation & configuration on test & production environment | Installation of country specific patch |  |  | 1 | 1360
MIC-CUST Import | US | Installation & configuration on test & production environment | Configuration of MIC-CUST® Import on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 3 | 4080
MIC-CUST Import | US | Installation & configuration on test & production environment | Configuration of MIC NCTS CE on test & production environment |  | Assumption: 1 company/plant combination ¦ configuration based on process description | 0 | 0
MIC-CUST Import | US | Installation & configuration on test & production environment | Setup of user and security settings for country on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC-CUST Import | US | Installation & configuration on test & production environment | Configuration of MIC-GTCS for global trade content services |  | dynamic list of values for DE | 0 | 0
MIC-CUST Import | US | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 1 | 1360
MIC-CUST Import | US | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated Integration Tests of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 1 | 1360
MIC-CUST Import | US | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST Import | US | Authority communication | Setup of authority communication for MIC-CUST Import (for SaaS solution) |  |  | 3 | 4080
MIC-CUST Import | US | Authority communication | Support at the setup of authority communication for MIC-CUST Import (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 3 | 4080
MIC-CUST Import | US | Authority communication | Creating and sending of test messages for MIC-CUST Import to the authorities |  | valid for SaaS and On-Premises solution | 1.5 | 2040
MIC-CUST Import | US | Authority communication | Setup of authority communication for MIC-NCTS CE (for SaaS solution) |  |  | 3 | 4080
MIC-CUST Import | US | Authority communication | Support at the setup of authority communication for MIC-NCTS CE (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 3 | 4080
MIC-CUST Import | US | Authority communication | Creating and sending of test messages for MIC-NCTS CE to the authorities |  | valid for SaaS and On-Premises solution | 1.5 | 2040
MIC-CUST Import | US | Data migration | Migration of part data |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | US | Data migration | Migration of addresses |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Import | US | Overall business process test on test & production environment | Definition of business process test cases (MIC-CUST Import) |  | Assumption: based on business cases defined in process description | 2 | 2720
MIC-CUST Import | US | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-CUST Import) |  |  | 3 | 4080
MIC-CUST Import | US | Overall business process test on test & production environment | Definition of business process test cases (MIC-NCTS CE) |  | Assumption: based on business cases defined in process description | 2 | 2720
MIC-CUST Import | US | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-NCTS CE) |  |  | 3 | 4080
MIC-CUST Import | US | Training and Go-Live Support | CWT (Client Walk Through) |  | Assumption: not needed; covered with user training | 0 | 0
MIC-CUST Import | US | Training and Go-Live Support | Key User Training - MIC-CUST® Import |  | 1,5 out of 2,5 days are for preparation and wrap-up activities ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 2.5 | 3200 |  |  | 2.5 | days |  |  | 1
MIC-CUST Import | US | Training and Go-Live Support | Support at UAT (User Acceptance Test) |  | Assumption: 3 weeks, 1 day per week | 4 | 5120 |  |  | 3 | weeks | 1 | day per week
MIC-CUST Import | US | Training and Go-Live Support | Go-Live Support |  | 1 trip estimated | 3 | 3840 | [8 empty] | 1
MIC-CUST Import | US | Training and Go-Live Support | Service Transition |  |  | 2 | 2560
MIC-CUST Export | per Country | Design | Requirements Definition |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap-up | 6 | 9120 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC-CUST Export | per Country | Design | Process Design & Description (MIC-CUST) |  | high-level project scope, project assumptions & dependencies, workflow/big picture, description of processes per business case incl. system integration, filing process to/from authorities, supplements, etc. | 2 | 3040
MIC-CUST Export | per Country | Design | Functional Specification (MIC-CUST) |  | company/plant structure, data source mapping, specification of customizing, definition and/or specification of reports, defaulting, etc. | 2 | 3040
MIC-CUST Export | per Country | Design | Process Design & Description (MIC-NCTS) |  | project assumptions & dependencies, workflow/big picture, description of processes per business case incl. system integration, filing process to/from authorities, etc. | 2 | 3040
MIC-CUST Export | per Country | Design | Functional Specification (MIC-NCTS) |  | data source mapping, specification of customizing, definition and/or specification of reports, defaulting, etc. | 1 | 1520
MIC-CUST Export | per Country | Installation & configuration on test & production environment | Installation of country specific patch |  |  | 1 | 1360
MIC-CUST Export | per Country | Installation & configuration on test & production environment | Configuration of MIC-CUST® Export on test & production environment |  | Assumption 1 company/plant combination | 1.5 | 2040
MIC-CUST Export | per Country | Installation & configuration on test & production environment | Configuration of MIC-NCTS CR on test & production environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC-CUST Export | per Country | Installation & configuration on test & production environment | Setup of user and security settings for country on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC-CUST Export | per Country | Installation & configuration on test & production environment | Configuration of MIC-GTCS for global trade content services; dynamic list of values for DE |  | Assumption: configuration is already done for MIC-CUST® Import | 0 | 0
MIC-CUST Export | per Country | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configurations of existing interface to MIC-CUST® Export (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 0.5 | 680
MIC-CUST Export | per Country | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated Integration Tests of existing interface to MIC-CUST® Export (see "MIC Interfaces") concerning the extraction of the country specific import data |  |  | 1 | 1360
MIC-CUST Export | per Country | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST Export | per Country | Authority communication | Setup of authority communication for MIC-CUST Export (for SaaS solution) |  | Assumption: setup is already done for MIC-CUST® Import | 0 | 0
MIC-CUST Export | per Country | Authority communication | Support at the setup of authority communication for MIC-CUST Export (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software; Assumption: setup / support is already done for MIC-CUST® Import | 0 | 0
MIC-CUST Export | per Country | Authority communication | Creating and sending of test messages for MIC-CUST Export to the authorities |  | valid for SaaS and On-Premises solution | 1 | 1360
MIC-CUST Export | per Country | Authority communication | Setup of authority communication for MIC-NCTS CR (for SaaS solution) |  | Assumption: setup is already done for MIC-NCTS CE | 0 | 0
MIC-CUST Export | per Country | Authority communication | Support at the setup of authority communication for MIC-NCTS CR (for On-Premises solution) |  | For the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software; Assumption: setup / support is already done for MIC-CUST® Import | 0 | 0
MIC-CUST Export | per Country | Authority communication | Creating and sending of test messages for MIC-NCTS CR to the authorities |  | valid for SaaS and On-Premises solution | 0.5 | 680
MIC-CUST Export | per Country | Data migration | Migration of part data |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Export | per Country | Data migration | Migration of addresses |  | Assumption: already done for MIC CUST Basic Setup | 0 | 0
MIC-CUST Export | per Country | Overall business process test on test & production environment | Definition of business process test cases (MIC-CUST Export) |  | Assumption: based on business cases defined in process description | 1 | 1360
MIC-CUST Export | per Country | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-CUST Export) |  |  | 2 | 2720
MIC-CUST Export | per Country | Overall business process test on test & production environment | Definition of business process test cases (MIC-NCTS CR) |  | Assumption: based on business cases defined in process description | 1 | 1360
MIC-CUST Export | per Country | Overall business process test on test & production environment | Execution and analysis of defined business process tests (MIC-NCTS CR) |  |  | 1 | 1360
MIC-CUST Export | per Country | Training and Go-Live Support | CWT (Client Walk Through) |  | Assumption: not needed; covered with user training | 0 | 0
MIC-CUST Export | per Country | Training and Go-Live Support | Key User Training - MIC-CUST® Export |  | 1 out of 2 days are for preparation and wrap-up activities ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 2 | 2560 |  |  | 2 | days |  |  | 1
MIC-CUST Export | per Country | Training and Go-Live Support | Support at UAT (User Acceptance Test) |  | Assumption: 3 weeks 1 day per week | 3 | 3840 |  |  | 3 | weeks | 1 | day per week
MIC-CUST Export | per Country | Training and Go-Live Support | Go-Live Support |  | 1 trip estimated | 3 | 3840 | [8 empty] | 1
MIC-CUST Export | per Country | Training and Go-Live Support | Service Transition |  |  | 1 | 1280
MIC-CUST | Stocks per Proc.&Ctry. | Design | Requirements Definition |  | Assumptions: 2 experts, 2 days workshop on-site, 2 days preparation & wrap up | 6 | 9120 | 1 | workshop | 2 | days | 2 | MIC expert(s)
MIC-CUST | Stocks per Proc.&Ctry. | Design | Process Design & Description |  | high-level project scope, project assumptions & dependencies, workflow/big picture, description of processes per business case incl. system integration, filing process to/from authorities, supplements, etc. | 4 | 6080
MIC-CUST | Stocks per Proc.&Ctry. | Design | Functional Specification |  | company/plant structure, data source mapping, specification of customizing, definition and/or specification of reports, defaulting, etc. | 3 | 4560
MIC-CUST | Stocks per Proc.&Ctry. | Installation & configuration on test & production environment | Installation of country specific patch |  |  | 1 | 1360
MIC-CUST | Stocks per Proc.&Ctry. | Installation & configuration on test & production environment | Configuration of MIC-CUST® Stocks for Customs Procedure and Country on test & production environment |  | Assumption 1 company/plant combination | 4 | 5440
MIC-CUST | Stocks per Proc.&Ctry. | Installation & configuration on test & production environment | Setup of user and security settings for country on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC-CUST | Stocks per Proc.&Ctry. | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configuration & System Integration Tests of existing interface to MIC-CUST® Import (see "MIC Interfaces") concerning the extraction of the country specific import data |  | Assumption: Interface configuration already done for CUST Import | 1.5 | 2040
MIC-CUST | Stocks per Proc.&Ctry. | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configuration & System Integration Tests of existing interface to MIC-CUST® Export (see "MIC Interfaces") concerning the extraction of the country specific export data |  | Assumption: Interface configuration already done for CUST Export | 1.5 | 2040
MIC-CUST | Stocks per Proc.&Ctry. | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configuration & System Integration Tests of existing interface to MIC-CUST® for stock entries (see "MIC Interfaces") concerning the extraction of the country specific data |  |  | 1.5 | 2040
MIC-CUST | Stocks per Proc.&Ctry. | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configuration & System Integration Tests of existing interface to MIC-CUST® for stock removals (see "MIC Interfaces") concerning the extraction of the country specific data |  |  | 1.5 | 2040
MIC-CUST | Stocks per Proc.&Ctry. | Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Estimated configuration & System Integration Tests of existing interface to MIC-CUST® for BOMs (see "MIC Interfaces") concerning the extraction of the country specific data |  |  | 0 | 0
MIC-CUST | Stocks per Proc.&Ctry. | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST | Stocks per Proc.&Ctry. | Authority communication | Creating and sending of test messages to the authorities |  |  | 1 | 1360
MIC-CUST | Stocks per Proc.&Ctry. | Data migration |  |  | Efforts for the migration of stocks need to be analyzed individually and are excluded in this quote | 0 | 0
MIC-CUST | Stocks per Proc.&Ctry. | Overall business process test on test & production environment | Definition of business process test cases |  | Assumption: based on business cases defined in process description | 2 | 2720
MIC-CUST | Stocks per Proc.&Ctry. | Overall business process test on test & production environment | Execution and analysis of defined business process tests |  |  | 3 | 4080
MIC-CUST | Stocks per Proc.&Ctry. | Training and Go-Live Support | CWT (Client Walk Through) |  | Assumption: not needed; covered with user training | 0 | 0
MIC-CUST | Stocks per Proc.&Ctry. | Training and Go-Live Support | Key User Training |  | 1 out of 2 days are for preparation and wrap-up activities ¦ 1 trip estimated; MIC Standard User Guide will be used; Handout for Key-User Training will be provided | 3 | 3840 |  |  | 2 | days |  |  | 1
MIC-CUST | Stocks per Proc.&Ctry. | Training and Go-Live Support | Support at UAT (User Acceptance Test) |  | Assumption: 3 weeks 1 day per week | 3 | 3840 |  |  | 3 | weeks | 1 | day per week
MIC-CUST | Stocks per Proc.&Ctry. | Training and Go-Live Support | Go-Live Support |  | 1 trip estimated | 3 | 3840 | [8 empty] | 1
MIC-CUST | Stocks per Proc.&Ctry. | Training and Go-Live Support | Service Transition |  |  | 1 | 1280
MIC-CUST GTDC | Global Trade Data Chain | Design | Analysis & Process Description |  |  | 1 | 1520
MIC-CUST GTDC | Global Trade Data Chain | Installation & configuration on test & production environment | Configuration of master data MIC-CUST® GTDC for 2 countries (1 country Export, 1 country Import) on test environment |  | Assumption 1 company/plant combination | 1 | 1360
MIC-CUST GTDC | Global Trade Data Chain | Installation & configuration on test & production environment | Configuration of master data MIC-CUST® GTDC for 2 countries (1 country Export, 1 country Import) on production environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC-CUST GTDC | Global Trade Data Chain | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST GTDC | Global Trade Data Chain | Overall business process test on test & production environment | Definition of test cases |  |  | 0.5 | 680
MIC-CUST GTDC | Global Trade Data Chain | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 2 | 2720
MIC-CUST GTDC | Global Trade Data Chain | Training and Go-Live Support | Go-Live Support - MIC-CUST® GTDC - Key user |  |  | 1 | 1280
MIC-CUST GTDC | Global Trade Data Chain | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC-CUST GUM | Guarantee Management | Design | Workshop |  | 1 Workshop à 0,5 days; 0,5 days preparation and wrap up; 1 trip estimated | 1 | 1520 | 1 | workshop | 0.5 | days |  |  | 1
MIC-CUST GUM | Guarantee Management | Design | Process Description |  |  | 0.5 | 760
MIC-CUST GUM | Guarantee Management | Installation & configuration on test & production environment | Setup of MIC-CUST® GUM on test environment |  |  | 0.5 | 680
MIC-CUST GUM | Guarantee Management | Installation & configuration on test & production environment | Setup of MIC-CUST® GUM on production environment |  |  | 0.25 | 340
MIC-CUST GUM | Guarantee Management | Installation & configuration on test & production environment | Configuration of master data on test environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC-CUST GUM | Guarantee Management | Installation & configuration on test & production environment | Configuration of master data on production environment |  | Assumption 1 company/plant combination | 0.25 | 340
MIC-CUST GUM | Guarantee Management | Installation & configuration on test & production environment | Setup of user and security settings on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC-CUST GUM | Guarantee Management | Installation & configuration on test & production environment | Setup of user and security settings for country on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC-CUST GUM | Guarantee Management | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST GUM | Guarantee Management | Overall business process test on test & production environment | Definition of test cases |  |  | 0.25 | 340
MIC-CUST GUM | Guarantee Management | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 0.5 | 680
MIC-CUST GUM | Guarantee Management | Training and Go-Live Support | Key User Training - MIC-CUST® GUM incl. electronic documentation |  | 0,25 out of 0,5 days are for preparation and wrap-up activities; remote | 0.5 | 640 |  |  | 0.5 | days
MIC-CUST GUM | Guarantee Management | Training and Go-Live Support | Support at UAT (User Acceptance Test) - MIC-CUST® GUM Key User |  | Assumption: 1 weeks 0,5 days per week | 0.5 | 640 |  |  | 1 | week | 0.5 | days per week
MIC-CUST GUM | Guarantee Management | Training and Go-Live Support | Go-Live Support - MIC-CUST® GUM |  | remote | 0.5 | 640
MIC-CUST | Rollout per Location | Design | Workshop |  | 1 Workshop à 1 day to ensure that existing MIC processes can be rolled-out; 1 trip estimated | 1 | 1520 | 1 | workshop | 1 | day |  |  | 1
MIC-CUST | Rollout per Location | Design | Update of existing process description |  |  | 0.5 | 760
MIC-CUST | Rollout per Location | Installation & configuration on test & production environment | Setup of user and security settings on test & production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC-CUST | Rollout per Location | Installation & Configuration of interfaces on test- and production environment | 1 interface from <company> to MIC-CUST® Import for invoices (analysis, documentation, scripts for upload & job scheduling) via MIC Webservices |  | Assumption: Existing interfaces can be re-used for other locations without modification | 1 | 1360
MIC-CUST | Rollout per Location | Installation & Configuration of interfaces on test- and production environment | 1 interface from <company> to MIC-CUST® Export for dispatch data (analysis, documentation, scripts for upload & job scheduling) via MIC Webservices |  | Assumption: Existing interfaces can be re-used for other locations without modification | 1 | 1360
MIC-CUST | Rollout per Location | Installation & Configuration of interfaces on test- and production environment | 1 interface from <company> to MIC-CUST® for BOMs (analysis, documentation, scripts for upload & job scheduling) via MIC Webservices |  | Assumption: Existing interfaces can be re-used for other locations without modification | 1 | 1360
MIC-CUST | Rollout per Location | Installation & Configuration of interfaces on test- and production environment | 1 interface from <company> to MIC ALL for vendor and customer address data (analysis, documentation, scripts for upload & job scheduling, tests) via MIC Webservices |  | Assumption: Existing interfaces can be re-used for other locations without modification | 1 | 1360
MIC-CUST | Rollout per Location | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC-CUST | Rollout per Location | Data migration | Migration of stocks |  |  | 0.5 | 680
MIC-CUST | Rollout per Location | Overall business process test on test & production environment | Definition of test cases |  |  | 0.5 | 680
MIC-CUST | Rollout per Location | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 1 | 1360
MIC-CUST | Rollout per Location | Training and Go-Live Support | Training - MIC-CUST® - Key User |  | 0,5 out of 1 days are for preparation and wrap-up activities | 1 | 1280 |  |  | 1 | day
MIC-CUST | Rollout per Location | Training and Go-Live Support | Go-Live Support - MIC-CUST® |  | remote | 1 | 1280
MIC-CUST | Rollout per Location | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC INTRA | Basic Setup | Design | Workshop |  | 1 Workshop à 2 days; 1 day preparation and wrap up; 1 trip estimated | 3 | 4560 | 1 | workshop | 2 | days |  |  |  | 1
MIC INTRA | Basic Setup | Design | Process Description |  |  | 2 | 3040
MIC INTRA | Basic Setup | Design |  |  |  |  | 0
MIC INTRA | Basic Setup | Installation & configuration on test & production environment | Configuration of master data on test environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC INTRA | Basic Setup | Installation & configuration on test & production environment | Configuration of master data on production environment |  | Assumption 1 company/plant combination | 0.25 | 340
MIC INTRA | Basic Setup | Installation & configuration on test & production environment | Setup of user and security settings on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC INTRA | Basic Setup | Installation & configuration on test & production environment | Setup of user and security settings on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC INTRA | Basic Setup | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any AVL List specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC INTRA | Basic Setup | Integration tests | Support during integration tests |  |  | 1 | 1360
MIC INTRA | Basic Setup | Overall business process test on test & production environment | Definition of test cases |  |  | 1 | 1360
MIC INTRA | Basic Setup | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 2 | 2720
MIC INTRA | Basic Setup | Training and Go-Live Support | Key User Training - MIC INTRA incl. electronic documentation |  | (1 out of 2 days are for preparation and wrap-up activities); 1 trip estimated | 2 | 2560 |  |  | 2 | days |  |  | 1
MIC INTRA | Per Country | Installation & configuration on test & production environment | Configuration of master data MIC INTRA on test environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC INTRA | Per Country | Installation & configuration on test & production environment | Configuration of master data MIC INTRA on production environment |  | Assumption 1 company/plant combination | 0.25 | 340
MIC INTRA | Per Country | Installation & configuration on test & production environment | Setup of user and security settings for country on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC INTRA | Per Country | Installation & configuration on test & production environment | Setup of user and security settings for country on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC INTRA | Per Country | Installation & Configuration of interfaces on test- and production environment | Estimated configurations of interface concerning the extraction of the country |  | specific arrival / dispatch data and tests | 0.5 | 680
MIC INTRA | Per Country | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC INTRA | Per Country | Overall business process test on test & production environment | Definition of test cases |  |  | 0.5 | 680
MIC INTRA | Per Country | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 1 | 1360
MIC INTRA | Per Country | Training and Go-Live Support | Go-Live Support - MIC INTRA - Key user |  | remote | 0.5 | 640
MIC INTRA CONVERT | Per Country | Installation & configuration on test & production environment | Configuration of master data MIC INTRA CONVERT for 2 countries (1 country Export, 1 country Import) on test environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC INTRA CONVERT | Per Country | Installation & configuration on test & production environment | Configuration of master data MIC INTRA CONVERT for 2 countries (1 country Export, 1 country Import) on test environment |  | Assumption 1 company/plant combination | 0.25 | 340
MIC INTRA CONVERT | Per Country | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC INTRA CONVERT | Per Country | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 0.5 | 680
MIC INTRA CONVERT | Per Country | Training and Go-Live Support | Go-Live Support - MIC INTRA CONVERT - Key user |  |  | 0.5 | 640
MIC INTRA | Rollout per Location | Installation & configuration on test & production environment | Configuration of master data MIC INTRA on test environment |  | Assumption 1 company/plant combination | 0.25 | 340
MIC INTRA | Rollout per Location | Installation & configuration on test & production environment | Configuration of master data MIC INTRA on production environment |  | Assumption 1 company/plant combination | 0.25 | 340
MIC INTRA | Rollout per Location | Installation & configuration on test & production environment | Setup of user and security settings for country on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC INTRA | Rollout per Location | Installation & configuration on test & production environment | Setup of user and security settings for country on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC INTRA | Rollout per Location | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC INTRA | Rollout per Location | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 0.5 | 680
MIC EMCS | Basic Setup | Design | Workshop |  | 1 Workshop à 2 days; 1 day preparation and wrap up; 1 trip estimated | 3 | 4560 | 1 | workshop | 2 | days |  |  |  | 1
MIC EMCS | Basic Setup | Design | Process Description |  |  | 2 | 3040
MIC EMCS | Basic Setup | Design | Functional Specification |  |  | 1 | 1520
MIC EMCS | Basic Setup | Installation & configuration on test & production environment | Setup of MIC EMCS CR & CE on test environment |  |  | 1 | 1360
MIC EMCS | Basic Setup | Installation & configuration on test & production environment | Setup of MIC EMCS CR & CE on production environment |  |  | 0.5 | 680
MIC EMCS | Basic Setup | Installation & configuration on test & production environment | Configuration of master data MIC EMCS CR + CE on test environment |  | Assumption 1 company/plant combination | 1 | 1360
MIC EMCS | Basic Setup | Installation & configuration on test & production environment | Configuration of master data MIC EMCS CR + CE on production environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC EMCS | Basic Setup | Installation & configuration on test & production environment | Setup of user and security settings on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC EMCS | Basic Setup | Installation & configuration on test & production environment | Setup of user and security settings on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC EMCS | Basic Setup | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC EMCS | Basic Setup | Integration tests | Support during integration tests |  |  | 2 | 2720
MIC EMCS | Basic Setup | Overall business process test on test & production environment | Definition of test cases |  |  | 1 | 1360
MIC EMCS | Basic Setup | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 2 | 2720
MIC EMCS | Per Country | Design | Workshop |  | 1 Workshop à 2 days; 0,5 day preparation and wrap up; 1 trip estimated | 2.5 | 3800 | 1 | workshop | 2 | days |  |  |  | 1
MIC EMCS | Per Country | Design | Process Description |  |  | 1 | 1520
MIC EMCS | Per Country | Installation & configuration on test & production environment | Installation of country specifics on test environment |  |  | 1 | 1360
MIC EMCS | Per Country | Installation & configuration on test & production environment | Installation of country specifics on production environment |  |  | 0.5 | 680
MIC EMCS | Per Country | Installation & configuration on test & production environment | Configuration of master data MIC EMCS CR + CE for country on test environment |  | Assumption 1 company/plant combination | 1 | 1360
MIC EMCS | Per Country | Installation & configuration on test & production environment | Configuration of master data MIC EMCS CR + CE for country on production environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC EMCS | Per Country | Installation & configuration on test & production environment | Setup of user and security settings on test environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 1 | 1360
MIC EMCS | Per Country | Installation & configuration on test & production environment | Setup of user and security settings on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.5 | 680
MIC EMCS | Per Country | Installation & Configuration of interfaces on test- and production environment | Configuration of existing interfaces on test and production environment |  |  | 1 | 1360
MIC EMCS | Per Country | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC EMCS | Per Country | Authority communication | Support at the setup of authority communication |  | only require for On-Premises solution; for the On-Premises solution hardware and software for communication (varies from country to country) is not part of the MIC software | 1 | 1360
MIC EMCS | Per Country | Authority communication | Creating and sending of test messages to the authorities |  |  | 0.5 | 680
MIC EMCS | Per Country | Data migration |  |  | Assumption: no initial data migration required | 0 | 0
MIC EMCS | Per Country | Overall business process test on test & production environment | Definition of test cases |  |  | 1 | 1360
MIC EMCS | Per Country | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 2 | 2720
MIC EMCS | Per Country | Training and Go-Live Support | Key User Training - MIC-EMCS CR+CE incl. electronic documentation |  | 0,5 out of 1,5 days are for preparation and wrap-up activities; 1 trip estimated | 1.5 | 1920 |  |  | 1.5 | days |  |  | 1
MIC EMCS | Per Country | Training and Go-Live Support | Go-Live Support - MIC-CUST® Import - Key user |  | remote | 0.5 | 640
MIC EMCS | Per Country | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC Data Analytics | Basic Setup | Installation & configuration on test & production environment | Setup of MIC Data Analytics on production environment |  |  | 0.5 | 680
MIC Data Analytics | Basic Setup | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC Data Analytics | Basic Setup | Training and Go-Live Support | Key User Training - MIC-Data Analytics incl. Preparation + Training Video |  |  | 1 | 1280
MIC Data Analytics | Basic Setup | Training and Go-Live Support | Go-Live Support - MIC Data Analytics |  | Assumption: done remotely | 0.5 | 640
MIC Data Analytics | Per Dataset | Analysis and System Specification | Joint Review of Data Mapping |  | Assumption: 1 dataset included | 1 | 1520
MIC Data Analytics | Per Dataset | Installation & configuration on test & production environment | Setup & Configuration of Import DE dataset incl. 2 pre-defined dashboards |  | Assumption: Data is provided in the "German Authority" format | 0.5 | 680
MIC Data Analytics | Per Dataset | Installation & configuration on test & production environment | Setup of user and security settings on production environment |  | Assignment of functions - e.g. update/delete - to roles, assignment of users to roles | 0.25 | 340
MIC Data Analytics | Per Dataset | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC Data Analytics | Per Dataset | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 0.5 | 680
MIC SAP | Per MIC SAP Interface | Design | Process Description |  | Assumption: no workshops required | 1 | 1520
MIC SAP | Per MIC SAP Interface | Design | Functional Specification |  |  | 0.5 | 760
MIC SAP | Per MIC SAP Interface | Installation & configuration on test & production environment | Support for Installation of MIC SAP Interfaces on test environment |  |  | 0.5 | 680
MIC SAP | Per MIC SAP Interface | Installation & configuration on test & production environment | Support for Installation of MIC SAP Interfaces on production environment |  | Assumption: no support required from MIC | 0 | 0
MIC SAP | Per MIC SAP Interface | Installation & configuration on test & production environment | Configuration of MIC SAP Interface on test environment |  | Assumption 1 company/plant combination | 1 | 1360
MIC SAP | Per MIC SAP Interface | Installation & configuration on test & production environment | Configuration of MIC SAP Interface on production environment |  | Assumption 1 company/plant combination | 0.5 | 680
MIC SAP | Per MIC SAP Interface | Automation & customer-specific software adaptations |  |  | We assume that <company> uses MIC standard processes. Any <company> specific software adaptations need to be analyzed and the workload estimated which may result in additional costs. | 0 | 0
MIC SAP | Per MIC SAP Interface | Automation scripts / Batch jobs | Support for Automation of SAP interface |  |  | 0.25 | 340
MIC SAP | Per MIC SAP Interface | Overall business process test on test & production environment | Definition of test cases |  |  | 0.25 | 340
MIC SAP | Per MIC SAP Interface | Overall business process test on test & production environment | Execution and analysis of system tests |  |  | 0.5 | 680
MIC SAP | Per MIC SAP Interface | Training and Go-Live Support | Go-Live Support |  |  | 0.5 | 640
MIC SAP | Per MIC SAP Interface | Training and Go-Live Support | Service Transition |  |  | 0 | 0
MIC SaaS | General Tasks SaaS | Installation & configuration on test & production environment | Basic setup of test environment |  |  | 2 | 2720
MIC SaaS | General Tasks SaaS | Installation & configuration on test & production environment | Basic setup of production environment |  |  | 1 | 1360
MIC SaaS | General Tasks SaaS | Installation & configuration on test & production environment | Setup of user and security settings |  | Single sign-on (SSO), user setup | 1 | 1360

## Modules
Module | Scope Full-Name | Summary Full-Name | Module AddOn | ModScope-Name
MIC CCS | Basic Setup | Basic Setup for MIC CCS - Central Classification System | Central Classification System | MIC_CCS_Basic_Setup
MIC CCS | Basic Setup considering 1 country for Customs Tariff Classification | Basic Setup for MIC CCS Part Master considering 1 country for Customs Tariff Classification (MIC CCS CTC) | Part Master only | MIC_CCS_Basic_Setup_Part_Mast
MIC CCS CTC | Per Country | MIC CCS CTC - Customs Tariff Classification per available Country (5) Country Subscription for MIC CCS CTC incl. Tariff Content | Customs Tariff Classification | MIC_CCS_CTC_Per_Country
MIC DPS |  | MIC DPS - Denied Party Screening Global Subscription incl. Sanction List Content | Denied Party Screening | MIC_DPS_Denied_Party_Screening
MIC ECM | Basic Setup | Basic Setup for MIC ECM - Export Control Management | Export Control Management | MIC_ECM_Basic_Setup
MIC CCS ECC | Per Regime | MIC CCS ECC - Export Control Classification per available Regime (6) Subscription per regime for MIC CCS ECC incl. Commodity List Content | Export Control Classification | MIC_CCS_ECC_Per_Regime
MIC ECM | Per Regime | MIC ECM - Export Control Management per available Regime (8) Subscription per Regime incl. Export Control Content | Export Control Management | MIC_ECM_Per_Regime
MIC ECM | Rollout per Additional Location |  | Origin Calculation System | MIC_ECM_Rollout_per_Location
MIC OCS | Basic Setup | Basic Setup for MIC OCS - Origin Calculation System | Preferential Management | MIC_OCS_Basic_Setup
MIC OCS SCS | Global Supplier Solicitation via MIC OCS Supplier Webportal | MIC OCS SCS - Basic Activities for Supply Chain Solicitation (7) Supplier Solicitation via MIC OCS Supplier Web Portal EU Subscription | Supply Chain Solicitaion | MIC_OCS_SCS_Supply_Chain_Soli
MIC OCS | 1 Bundle including <#> <region> FTAs | Per each available Free Trade Agreement (FTA) or FTA Bundle (9) Note: Depending on the FTAs it is possible to bundle several physical FTAs into 1 configured FTA in MIC OCS. | per Free Trade Agreement (FTA) Bundle | MIC_OCS_Per_FTA_Bundle
MIC OCS |  |  | per Free Trade Agreement (FTA) | MIC_OCS_Per_FTA
MIC OCS | MIC OCS SCS and MIC OCS CALC Rollout per Additional Region |  | Origin Calculation System | MIC_OCS_Rollout_per_Region
MIC OCS CALC |  | MIC OCS CALC - Basic Activities for Origin Calculation (7) EU Subscription | Origin Calculation | MIC_OCS_CALC_Origin_Calculati
MIC OCS | MIC OCS SCS and MIC OCS CALC Rollout per Additional Location |  | Origin Calculation System | MIC_OCS_Rollout_per_Location
MIC-CUST | Basic Setup | Basic Setup for MIC-CUST® - Global Customs Filing | Global Customs Filing | MIC_CUST_Basic_Setup
MIC-CUST | Per Available Country | MIC-CUST® Import & MIC NCTS CE per Available Country (7) Electronic filing of simplified customs declarations | Import & MIC NCTS CE | MIC_CUST_Import_per_Country
MIC-CUST | Per Available Country Assumptions: <TBD> | MIC-CUST® Export & MIC NCTS CR per Available Country (7) Electronic filing of simplified customs declarations | Export & MIC NCTS CR | MIC_CUST_Export_per_Country
MIC-CUST | Per Customs Procedure (e.g. IPR, OPR, BWH) and Available Country | MIC-CUST® per Special Procedure and Available Country (7) Electronic filing of simplified customs declarations | Stocks | MIC_CUST_Stocks_per_Proc__Ctr
MIC-CUST GTDC | Per Country Combination | MIC-CUST® GTDC per 2 Countries Global Trade Data Chain - Generation of Import Declarations from Export Declarations | Global Trade Data Chain | MIC_CUST_GTDC_Global_Trade_Da
MIC-CUST GUM |  | MIC-CUST® GUM - Gurantee Management | Guarantee Management | MIC_CUST_GUM_Guarantee_Manage
MIC-CUST | Rollout per Additional Location |  | Global Customs Filing | MIC_CUST_Rollout_per_Location
MIC INTRA | Basic Setup | Basic Setup for MIC-INTRA - Instrastat Filing | Intrastat Filing | MIC_INTRA_Basic_Setup
MIC INTRA | Rollout per Country - 1 Location | MIC INTRA Arrival & Dispatch (per EU Country) 1 Location |  | MIC_INTRA_Per_Country
MIC INTRA CONVERT | Conversion of Dispatch Data into Arrivial Data - 1 Location | MIC INTRA CONVERT per 2 EU Countries | per 2 EU Countries | MIC_INTRA_CONVERT_Per_Country
MIC INTRA | Rollout per Additional Location |  |  | MIC_INTRA_Rollout_per_Location
MIC EMCS | Basic Setup for Consignor and Consignee | Basic Setup for MIC-EMCS - Excise Movement and Control System | Excise Movement and Control System | MIC_EMCS_Basic_Setup
MIC EMCS | Per Available Country | MIC EMCS per Country |  | MIC_EMCS_Per_Country
MIC Data Analytics | Basic Setup | Data Analytics - Basic Setup and Operation incl. Apache Superset Visualization Platform |  | MIC_Data_Analytics_Basic_Setup
MIC Data Analytics | Per Dataset | MIC Data Analytics & Visualization ¦ <Module/Country> Dataset • Subscription for one legal enitity • Setup of 1 dataset incl. 2 pre-defined dashboards • incl. 50GB storage (Assumption: Data is provided in the "<Format: e.g. German Authority>" format & layout) |  | MIC_Data_Analytics_Per_Dataset
MIC SAP |  |  | Interface | MIC_SAP_Per_MIC_SAP_Interface
MIC SaaS |  |  | General Tasks SaaS (One Time) | MIC_SaaS_General_Tasks_SaaS
MIC-CUST Import | DE | MIC-CUST® Import DE - Customs Filing Germany | DE | MIC_CUST_Import_DE

## Footnotes
Footnote_Num | Footnote_Content
1 | (1) Country Specific Add-On's cover the communication (message creation either electronic and/or paper) with authorities in the requested country and for the requesting MIC module (see Service Level Agreement).
2 | (2) MIC offers maintenance (covers legal changes) for Country Specific Add On's in countries MIC has availabe at the time of request for a Country Specific Add-On.
3 | (3) 1st Level Support will be handled by <company> key users. 2nd & 3rd level application support will be provided by MIC.
4 | (4) A detailed list of the services included in the Monthly Fee is available in section 'SaaS'.
5 | (5) The costs for the tariff contents depend on the country (see also 'Global Trade Content Services'). We have included content at an annual subscription fee of 6.000 EUR - in case the tariff for a specific country is more expensive the corresponding surcharge will be applied.
6 | (6) It is assumed that MIC CCS CTC is already in use.
7 | (7) It is assumed that the tariff content is already available for the corresponding MIC CCS subscription for this country. If this is not the case the content fee for the applicable tariff content will be added to the service fee.
8 | (8) The workload per export control regime can vary depending on the complexity of the regime. In general our experience is that with every configured export control regime the workload for setup goes down due to synergies. The mentioned workload is an average value based on experience. MIC supports in setting up and maintaining regulations and licenses including rules used for <company> business as part of the 2nd &3rd Level Application Support. In any case approval is required by <company> before it is moved to production.
9 | (9) The workload per FTA can vary depending on the complexity of the FTA. In general our experience is that with every used FTA the workload for setup goes down due to synergies. The mentioend workload is an average value based on experience. MIC supports in setting up and maintaining rules of origin (list criteria) used for <company> business as part of the 2nd &3rd Level Application Support. In any case approval is required by <company> before it is moved to production.
10 | (10) Example: ▪ Parameters - minimum volume: 5.000 declarations / year - actually processed volume: 8.500 declarations / year ▪ Invoicing - in advance: 5.000 declarations * 9,63 € - in addition: 2.500 declarations * 9,63 € + 1.000 declarations * 6,70 €

## Roles
Role | Daily Rate
Senior Manager | 1600
Project Manager, Business Analyst | 1520
Developer, System Engineer | 1360
Trainer, Support Engineer | 1280

## Phases
Phase | Comment | Role | Daily Rate
Senior management |  | Senior Manager | 1600
Project management and project documentation |  | Project Manager, Business Analyst | 1520
Design |  | Project Manager, Business Analyst | 1520
Installation & configuration on test & production environment |  | Developer, System Engineer | 1360
Automation & customer-specific software adaptations |  | Developer, System Engineer | 1360
Integration tests |  | Developer, System Engineer | 1360
Overall business process test on test & production environment |  | Developer, System Engineer | 1360
Data Migration |  | Developer, System Engineer | 1360
Training and Go-Live Support | Train the Trainer (1 Trainer for all sites limited to 5 users). It is assumed that the participants are customs experts. | Trainer, Support Engineer | 1280
Authority communication |  | Developer, System Engineer | 1360
Installation / configuration of interfaces on test- and production environment - OPTIONAL (if existing interfaces can be reused) | Assumption: Existing interfaces can be reused | Developer, System Engineer | 1360
Installation & Configuration of interfaces on test- and production environment | Assumption: Existing interfaces can be reused | Developer, System Engineer | 1360
Automation scripts / Batch jobs |  | Developer, System Engineer | 1360
Analysis and System Specification |  | Project Manager, Business Analyst | 1520